Request for Proposal

Curriculum Design and Development for a Federal Project

RFP 01-2026

March 19, 2026

NRECA Research (NRECA)

CONFIDENTIALITY

This document has been prepared by NRECA and is being given to Respondent, in consideration of Respondent’s agreement to treat the information contained within this document and related business discussions as confidential, to provide Respondent with an opportunity to respond to NRECA’s requirements as contained further herein. The information enclosed in this document is proprietary to NRECA. NRECA is not conveying any ownership to any party by disclosing this information. By accepting this document, Respondent agrees that Respondent will:  (1) treat this information as confidential; (2) not allow any other person or entity to see it or use it; and (3) not use it in any way other than to prepare the requested response.

TABLE OF CONTENTS

1.0	INTRODUCTION	1

1.1	Objective	1

1.2	NRECA Overview	1

1.3	Timetable	1

2.0	REQUIREMENTS	2

2.1	Background and Goals	2

2.2	Functional and Technical Requirement	2

3.0	RESPONSE PROCEDURES	6

3.1	Staff and Agents	6

3.2	Response Protocol	6

3.4	Response Format	6

1.0	INTRODUCTION

1.1	Objective

The objective of this document is to solicit responses that will provide the NRECA Research (“NRECA”) with a Subcontractor to develop and design curriculum resources around Advanced Overhead Conductors (“AOHC”) and expand their overall utilization. Responses to this document are expected to propose a complete solution that meets all the stated requirements.

1.2	NRECA Overview

National Rural Electric Cooperative Association (“NRECA”) is the national service organization for nearly nine hundred eight (980) not-for-profit rural electric cooperatives and public power districts providing retail electric service to over forty-two (42) million people in forty-eight (48) states and whose retail sales account for approximately seventeen (17) percent of total electricity sales in the United States. NRECA’s members include consumer-owned local distribution systems – the vast majority – and sixty-four (64) generation and transmission (“G&T”) cooperatives who supply wholesale power to their distribution cooperative owner-members. Distribution and G&T cooperatives share an obligation to serve their members by providing safe, reliable and affordable electric service.

NRECA provides legislative, legal, and regulatory services through the dues-supported revenues as well as fee-based services associated with group insurance, pension, employee benefits / compensation, savings / investments, market research, training and certification, energy and management consulting, subscriptions to various publications, and advertising. NRECA and its member cooperatives also support electric cooperative-specific and environmental research and administer a program of technical advice and assistance with the electrification of developing countries around the world. NRECA has offices in Arlington, Virginia, and Lincoln, Nebraska.

NRECA Research (“NRECA”) is a wholly owned subsidiary of the National Rural Electric Cooperative Association and manages all of NRECA’s federal research contracting efforts.

1.3	Timetable

NRECA expects to adhere to the timetable shown below. It should be noted, however, that the Target Dates are approximate and subject to change.

| Activity | Target Dates |
| --- | --- |
| Release of Request for Proposal | March 19, 2026 |
| Intent to Bid is Due | April 05, 2026 |
| Questions to RFP are accepted. | April 12, 2026 |
| Answers to Questions are issued | April 14, 2026 |
| Proposals Due | April 20, 2026 |

2.0	REQUIREMENTS

  - Background and Goals

NRECA is participating in a Us Government federal project where the project’s high-level goal is to create awareness of the techno-economic advantages of AOHC and expand their overall utilization. The Project team will meet this goal through completion of three (3) key objectives:

Objective 1: Cost-effective improvements in resilience, reliability, and transfer capacity - Improve the reliability, resilience, and transfer capacity of participating transmission networks, by rebuilding/reconductoring existing or building new transmission lines to complete a redundant loop, at lower total by leveraging the techno-economic advantages of AOHC conductors.

Objective 2: Shift in grid design process - Drive a fundamental shift in grid designs by developing and contrasting AOHC and Aluminum  Conductor Steel Reinforced (“ACSR”) based design alternatives to show how to leverage the benefits of AOHC. Integrate Transmission Siting Tool to improve designs, efficiently avoid sensitive areas, improve community acceptance, and reduce costs.

Objective 3: Increased utilization of AOHC - Drive increased utilization of AOHC by expanding utility familiarity and comfort level with AOHC, its uses, and benefits by issuing a AOHC Technical Design Bulletin that documents how to fully leverage AOHC and by issuing an AOHC Use Cases Report that documents real-world implementation of AOHC.

As part of this project and to achieve these objectives, NRECA is seeking a Subcontractor to provide assistance in creating and designing curriculum resources around advanced conductors for both a virtual and in-person audience for one of NRECA’s federal projects

2.2	Functional and Technical Requirement

Role in the Project:

Subcontractor shall report to NRECA and provide the necessary support and services as defined by the scope of activities below. Subcontractor shall track budget in accordance with the Federal Assistance Reporting requirements and provide NRECA with technical and financial status reporting on the project activities.

Scope of Activities:

NRECA and its project partners are seeking support and services from qualified Subcontractors to develop and design curriculum resources around AOHC for both virtual and in-person audiences. Subcontractor shall track budget in accordance with the Federal Assistance Reporting requirements and provide NRECA Research with technical and financial status reporting on the project activities.

Subcontractor shall provide support for the tasks defined below. Services shall be performed by the key expert(s). These tasks shall include the following, and are not limited to:

Task 1: Kickoff meeting and Project Management:

- Subtask 1.1: Kickoff meeting:

  - Subcontractor shall support NRECA and convene a virtual kickoff meeting to review roles and responsibilities of each team member; project expectations and timeline, tasks, and reporting requirements.

  - Subcontractor shall deliver minutes by the fifth (5th) business day from the meeting date.

- Subtask 1.2: Subcontractor Project Management Plan (“PMP”):

  - Within fifteen (15) days of signing the Subcontractor agreement with NRECA, Subcontractor shall submit a PMP to NRECA. The PMP shall be revised and resubmitted as often as necessary, during the project, to capture any major/significant changes to the planned approach, budget, key personnel, major resources, etc. Subcontractor shall manage and direct the project in accordance with the accepted PMP to meet all technical, schedule, and budget objectives and requirements.

  - Subcontractor, in consultation with NRECA, shall coordinate activities to effectively accomplish the work.

  - Subcontractor ensures that project plans, results, and decisions are appropriately documented, and that project reporting and briefing requirements are satisfied.

  - Subcontractor shall provide support to NRECA and the overall Project staff as needed and appropriate.

- Subtask 1.3: Project status updates and ad hoc meetings:

  - Subcontractor shall participate in monthly status calls along with any ad hoc meetings where information relevant to their tasks may be shared and discussed. If required, weekly status calls may be scheduled. Subcontractor shall deliver minutes by the fifth (5th) business day from the meeting date.

- Subtask 1.4: Travel:

  - Subcontractor shall be willing to travel and participate in workshops conducted by Electric Power Research Institute (‘EPRI”) and the Project team.

  - Subcontractor shall engage in on-site project meetings, evaluations, and training sessions to support curriculum development.

Task 2: Curriculum Development

Subcontractor shall be responsible for the following project Deliverables:

- Subtask 2.1:

  - Survey existing academic and professional curricula relevant to advanced conductors and reconductoring transmission lines.

  - Identify gaps where instructional content is required.

  - Prepare a report summarizing findings and recommendations for new curriculum development.

- Subtask 2.2:

  - Create curriculum modules to address gaps in existing academic and professional curricula for advanced conductors and the reconductoring of transmission lines.

  - Create syllabi, learning objectives, instructor guides, and other resources and materials for the modules. These modules shall be suitable for use in online courses at colleges and technical universities. Modules will be designed to support undergraduate instruction, graduate-level coursework, and workforce and professional development (adult learners).

  - Documentation for each module shall be created.

- Subtask 2.3:

  - Conduct pilot implementations of the modules in at least two (2) instruction settings, including undergraduate and graduate-level university courses and workforce or professional development (adult learning) environments, depending on the results of the gap analysis.

  - Collect student and instructors feedback during the pilot process.

  - Incorporate the feedback as appropriate in the modules.

  - Prepare a fifteen (15) page report summarizing the results of the curriculum pilot.

- Subtask 2.4:

  - Test online versions of the curriculum modules to fill gaps in existing academic and professional curricula relevant to reconductoring transmission lines.

  - Provide a lesson learned document.

- Subtask 2.5:

  - Subcontractor shall develop a broad dissemination strategy for the curriculum, including multi-media delivery.

  - Subcontractor should ensure that they engage in project-related training sessions and field visits, including, but not limited to, utility site visits and industry-led technical training. Such participation is intended to support technology familiarization and curriculum alignment. Participation requirements, timing, and modality (in-person or virtual) shall be determined by the Project Team and incorporated into the project schedule as needed.

  - Perform other assigned duties as needed.

In summary, Subcontractor shall provide support for Project Management, Curriculum Development, and Workforce Development. In addition, Subcontractor shall provide the necessary support to NRECA  on overall Project Management and the following Deliverables.

Deliverables:

| Tasks | Deliverables | Acceptable Format (not limited to) | Due dates |
| --- | --- | --- | --- |
| Subtask 1.1 | One (1) Kickoff meeting minutes and meeting minutes for 19 meeting | Word document | 5th business day after the contract execution and meeting minutes are due 5 business days from the meeting date. |
| Subtask 1.2 | Subcontractor Project Management Plan (PMP) | Word document | Within 15 days after the kickoff meeting. |
| Subtask 1.4 | Workshop and/or site visit minutes (EPRI, California) | Word document | Within 10 business days of the end of the workshop and/or site visit |
| Subtask 2.1 | Curriculum Survey Summary | Word document | June 30, 2026 |
| Subtask 2.1 | Gap Analysis Report | Word document | August 31, 2026 |
| Subtask 2.2 | Curriculum module design plan | Word document | January 15, 2027 |
| Subtask 2.2 | Instructor guide and student learning materials | Word document | May 31, 2027 |
| Subtask 2.3 | Feedback Collection Documentation | Word document | June 30, 2027 |
| Subtask 2.3 | A report summarizing the pilot test of each of the five modules in at least two university classes and developing online curricula. | Word document | September 30, 2027 |
| Subtask 2.3 | Deliver up to five (5) new curriculum modules ready to be used at colleges and technical universities through both in-person and virtual mediums | Word document | December 15, 2027 |
| Subtask 2.4 | Online modules test results | Word document | February 29, 2028 |
| Task 2.5 | Dissemination strategy report | Word document | April 28, 2028 |
|  | Final Report describing the dissemination of the curriculum and documenting the multi-media approach. | Word document | June 30, 2028 |

Briefing/Presentations

Subcontractor and NRECA may be asked to provide presentations on topics or related topics.

Reporting:

Reports were listed in the scope of activities and Deliverables are above. Administrative reporting requirements follow the Federal Assistance Reporting Checklist.

Period of Performance:

The anticipated period of performance is the date of contract execution through June 30, 2028.

Eligibility Requirement:

All participants providing a response must meet the following eligibility criteria:

- Minimum five years of relevant experience

- Ability to fulfill the services identified in the statement of work

- Agree to travel, attend trainings, and participate in workshops

- Legally registered entity

3.0	RESPONSE PROCEDURES

3.1	Staff and Agents

From the date that this document is issued until a determination is made and announced regarding the selection of one or more finalist Respondent(s), if applicable, contact between Respondent and individuals employed or otherwise engaged by NRECA is strictly prohibited. Following such selection, Respondent is similarly restricted from communicating with NRECA staff and agents until a contract is executed. The following exceptions to these restrictions are permitted:

- Written communication with the NRECA Contact as identified herein and related specifically to this document;

- Contacts with NRECA staff and agents which are approved in advance by the NRECA Contact;

- Those contacts made pursuant to any pre-existing obligation; and,

- contacts with NRECA staff present at sessions specified by the Timetable, if any.

Violations of these conditions may be considered sufficient cause to reject a response and / or Respondent selection irrespective of any other condition.

3.2	Response Protocol

Responses must be submitted to NRECA’s Workday Strategic Sourcing portal per the Schedule of Events/timetable contained herein. NRECA, at its discretion, may elect to return responses received after the deadline.

Responses should avoid including any identifying information regarding the firm or individuals that might be assigned to the tasks in response to section 2.2 of this RFP. This section should be easily extracted from the rest of the RFP response to assist NRECA Research in an impartial review of the RFP response.

All questions and general communications regarding this RFP should be directed via Workday Strategic Sourcing (“WSS”) portal.

Contact:

Tim Davis

703.907.5943 (Office)

timothy.davis@nreca.coop (E-mail)

NRECA reserves the right to reject any responses or, at NRECA's discretion, to solicit additional responses. NRECA may also accept or reject portions of a response.

3.4	Response Format and Evaluation Criteria

In order to assist in the fair and equitable evaluation of all responses, Respondents are being asked to adhere to the specific response format set forth below. Responses that deviate from the requested format may be classified as "non-responsive" at the discretion of NRECA and may be subject to disqualification.

Respondents’ proposals will be evaluated using a comprehensive set of criteria. To be considered, a Respondent must show in their proposal that they are able to meet the requirements described in Section 2.2 of this RFP as well as submit the written agreement to the terms and conditions included in the Subcontract Agreement.

Top priorities in the evaluation of the proposal are as follows:

- Respondent’s Viability - Experience, qualifications, background, and quality of Respondent’s staff assigned to the relationship.

- Technical Requirements - Ability to meet the requirements included in this RFP document.

- Negotiable Terms and Conditions - Are the contract redlines significant? Are there changes to DOE clauses?

- Cost of the Services

NRECA may contact any participant for clarification or additional information. But participants are advised that NRECA intends to evaluate the proposals based on the written submitted proposals.

| Section | Section Contents / Deliverables |
| --- | --- |
| Key Personnel | Provide Curriculum Vitae in PDF format for each proposed staff working on the project. |
| Company Background | Copy of Registration Certificate/Certificate of Incorporation and Company Profile |
| Relevant Experience | Supporting Information regarding similarity of previous work and extend to which Respondent successfully performed government contracting. Contact information for a minimum of three references with whom the participant has had a working relationship. NRECA may contact these individuals or companies. |
| Pricing | Provide pricing based on each deliverable |
| Proposal/Technical Response | Provide a clear, detailed description of your technical approach, methodology, and capabilities for completing the scope of the work. |
| Terms and Conditions | Provide detailed comments to NRECA’s Subcontract Agreement which will be the contracting document. |

NRECA will evaluate all submitted bids in accordance with the criteria outlined in this RFP. Following the selection of the winning bid, only the selected bidder will be required to provide Representations, Certifications, and Business Assurances, as well as proof of active SAM.gov registration prior to contract execution.

| Representations, Certifications and Business Assurances | NRECA requires the selected bidder to complete and submit their Representations, Certifications, and Business Assurances by following the link below and answering all 11 questions to the best of their ability. These responses must be provided prior to contract execution. https://www.cooperative.com/programs-services/bts/research/Pages/RepsCertsBusAssurances.aspx |
| --- | --- |
| Proof of SAM.gov Entity Registration | NRECA requires the selected bidder to have an active SAM.gov registration and to provide a copy of their entity registration prior to contract execution. Organizations not yet registered are encouraged to begin the process by visiting SAM.gov. SAM.gov Entity Registration page |
| W-9 Certification | Complete and submit signed W-9 form |